# SOP-L01 · Grant Application Preparation

Antragserstellung (DFG, IZKF, EU)

| Field | Value |
| --- | --- |
| SOP-Code | SOP-L01 |
| Series / Serie | L (Lead / Co-Lead policy) |
| Owner role / Owner-Rolle | Anträge + DFG-Reviews (r-grants) |
| Responsible / Verantwortlich | JB and HA (alternating primary author) |
| Cadence / Kadenz | Ad hoc (per grant deadline) |
| Status | v1 · 2026-07-28 |
| File / Datei | Documents/SOPs/2026-07-15_cRDM_SOP-L01_Grant-Application-Preparation.docx |

## 🎯 Purpose / Zweck

EN: Standardize the preparation of external grant applications (DFG, IZKF, EU, MWK, BMBF) where the cRDM contributes a support component — typically INF, Z02, or similar research-data-management infrastructure sections. Ensures consistent cRDM contributions and traceable filing.

DE: Vereinheitlicht die Vorbereitung externer Anträge (DFG, IZKF, EU, MWK, BMBF), bei denen die cRDM eine Unterstützungskomponente einbringt — typischerweise INF, Z02 oder ähnliche RDM-Infrastruktur-Sektionen. Sichert konsistente cRDM-Beiträge und nachvollziehbare Ablage.

## 🔔 When to run / Wann anwenden

- New grant call detected in SOP-B04 Networking-Calendar

- Consortium PI approaches cRDM with a proposal request

- Renewal of an existing INF/Z02 section

- Any request for a Letter of Support (LoS) from cRDM

## 👥 Roles (RACI)

| Role | Person(s) |
| --- | --- |
| Responsible (does the work) | Primary author (JB or HA, per monthly rotation) |
| Accountable (owns the outcome) | Both Co-Leads jointly |
| Consulted | Prof. Heinze (JMU strategic fit), Prof. Tovote (UKW strategic fit), Prof. Dandekar (bioinformatics infrastructure) |
| Informed | Content-Admin (for archival), Mareile (for calendar update) |

## 📥 Prerequisites / Voraussetzungen

- Grant call documentation available (PDF/URL)

- Consortium PI contact confirmed

- Current pricing model reviewed (Documents/PricingModels/)

- Latest cRDM boilerplate available (see filing location below)

## 📋 Procedure / Vorgehen

### 1. Intake (Day 0–2)

EN: Assess whether the request fits cRDM scope. If yes, create a folder Documents/Grants/{YYYY}_{acronym}/ and file the call documentation and initial correspondence there. Create a Deck card labelled grant-application.

DE: Prüfe, ob die Anfrage in den cRDM-Scope passt. Falls ja, Ordner Documents/Grants/{YYYY}_{acronym}/ anlegen und Call-Dokumentation sowie erste Korrespondenz dort ablegen. Deck-Karte mit Label grant-application anlegen.

### 2. Scope confirmation (Day 2–5)

Confirm with the consortium PI: - Exact cRDM component requested (INF, Z02, sub-section?) - Duration of the funded period - User counts, storage estimates, service package needed - Budget envelope for the cRDM section

### 3. Draft cRDM contribution (Day 5–14)

Author the cRDM section using: - Standard boilerplate: Documents/Grants/_boilerplate/cRDM-INF-boilerplate_{de,en}.docx - Pricing from current Documents/PricingModels/2026-Fee-Schedule.docx - Reference architecture from Projects/VRC/documents/architecture/ - Filled with consortium-specific details

Deliverables in this stage: - cRDM contribution text (typically 3-8 pages) - Cost/personnel table - Timeline aligned with consortium’s overall plan

### 4. Letter of Support (if requested)

If a Letter of Support is requested, use template Documents/Grants/_boilerplate/LoS-Template.docx. Both Co-Leads must sign. For institutional endorsement above cRDM, invoke SOP-L04 Institutional-Escalation.

### 5. Internal review (Day 14–20)

- Second Co-Lead reads the draft

- If budget > €50,000 or duration > 3 years: escalate to Prof. Heinze/Tovote for endorsement

- Correct MwSt/tax treatment for the funding body

### 6. Submission handover (Day 20–deadline)

Send finalized section to consortium PI at least 5 working days before their internal deadline. Include: - Final cRDM section (EN version if the call is EN, DE if DE) - Cost table - LoS (signed PDF) if applicable - Editable source file (.docx) so PI can integrate

### 7. Post-submission filing

- Copy the submitted version to Documents/Grants/{YYYY}_{acronym}/submitted/

- Log outcome in Documents/Grants/_tracker.xlsx (columns: acronym, PI, cRDM section pages, budget, submitted date, decision date, outcome)

- Update SOP-B04 Networking-Calendar with the expected decision date

- Move Deck card to Grants — submitted, waiting

## 📤 Outputs / Ergebnisse

- Filed cRDM contribution (Documents/Grants/{YYYY}_{acronym}/)

- Signed LoS (if applicable)

- Grant tracker entry

- Deck card in submitted state

- Calendar reminder for decision date

## ✅ Quality criteria / Qualitätskriterien

- Second Co-Lead has read and signed off

- Pricing aligned with current fee schedule (no ad-hoc numbers)

- Institutional endorsement obtained if required

- Sent to PI ≥ 5 working days before their deadline

- All files present in the grant folder

## 🔗 Related / Verwandt

- SOP-L02 — DFG Progress Report (follow-up if funded)

- SOP-L04 — Institutional Escalation Routing (for big-ticket applications)

- SOP-B04 — Networking Calendar (deadline tracking)

- SOP-B05 — RDM Contact Database (PI contacts)

## 📝 Notes / Anmerkungen

- Alternating authorship: JB and HA alternate as primary author month-by-month. Whoever is not primary this month does the second-Co-Lead review.

- Bilingual reality: Most DFG calls are DE, most EU calls are EN. Keep both boilerplate versions current.

- Boilerplate versioning: Update the boilerplate every 6 months (or when pricing changes). Version-stamp: cRDM-INF-boilerplate_de_2026-Q3.docx.

Change log

| Version | Date | Change |
| --- | --- | --- |
| v1 | 2026-07-28 | Initial version |