# SOP-L02 · DFG Progress Report

DFG-Zwischenbericht

| Field | Value |
| --- | --- |
| SOP-Code | SOP-L02 |
| Series / Serie | L (Lead / Co-Lead policy) |
| Owner role / Owner-Rolle | Anträge + DFG-Reviews (r-grants) |
| Responsible / Verantwortlich | JB and HA (per consortium ownership) |
| Cadence / Kadenz | Every 6 or 12 months per grant requirement |
| Status | v1 · 2026-07-28 |
| File / Datei | Documents/SOPs/2026-07-15_cRDM_SOP-L02_DFG-Progress-Report.docx |

## 🎯 Purpose / Zweck

EN: Prepare periodic progress reports (Zwischenberichte) to the DFG for ongoing consortium support where cRDM contributes as INF/Z02. Ensures reports are quantitatively backed, on time, and consistent across consortia.

DE: Erstellung periodischer Zwischenberichte an die DFG für laufende Konsortium-Unterstützung, bei denen cRDM als INF/Z02 beiträgt. Sichert quantitativ belegte, pünktliche und konsortium-übergreifend konsistente Berichte.

## 🔔 When to run / Wann anwenden

- 60 days before a DFG-required progress report is due (regular Zwischenbericht)

- Ad-hoc report request from consortium PI

- Annual accountability update to funder even if not formally required

## 👥 Roles (RACI)

| Role | Person(s) |
| --- | --- |
| Responsible | Co-Lead who owns the consortium (per Task Distribution Register) |
| Accountable | Both Co-Leads jointly |
| Consulted | Consortium PI (data validation) |
| Informed | Content-Admin (archival) |

## 📥 Prerequisites / Voraussetzungen

- Metadata Excel for the consortium is current (see SOP-A02)

- Access to Nextcloud usage metrics (storage, active users)

- Original grant application on hand for comparison

- Previous report(s) filed for consistency reference

## 📋 Procedure / Vorgehen

### 1. Deadline detection (T-90 days)

EN: SOP-B04 Networking-Calendar should already contain the deadline. If not, add it. Create Deck card labelled dfg-report with the deadline.

DE: Deadline sollte bereits im SOP-B04 Networking-Kalender stehen. Falls nicht, ergänzen. Deck-Karte mit Label dfg-report und Deadline anlegen.

### 2. Data collection (T-90 to T-60)

Collect quantitative metrics per consortium:

| Metric | Source |
| --- | --- |
| Active users | Nextcloud admin panel |
| Storage used vs. quota | Groupfolders app |
| Milestones hit vs. planned | Consortium PI |
| Training sessions delivered | HA’s log |
| Support tickets resolved | Content-Admin’s log |
| Publications acknowledging cRDM | PI + Google Scholar |
| Consortium-specific KPIs | Original grant application |

### 3. Draft narrative (T-60 to T-30)

Structure per DFG standard: 1. Berichtszeitraum — reporting period 2. Erreichte Ergebnisse — achievements (bullet points, quantitative) 3. Abweichungen vom Antrag — deviations from plan (with justification) 4. Erkenntnisse für die Community — outputs beyond the consortium 5. Ausblick — next reporting period plan 6. Personelle Änderungen — staff changes at cRDM

Length: 2–5 pages typical. Language: usually DE for DFG, follow original grant language.

### 4. Cross-consortium consistency check (T-30 to T-20)

If reports for multiple consortia are due within 60 days, review together to ensure: - Consistent framing of cRDM services - No contradictory claims about capacity - Reasonable acknowledgment attribution

### 5. Second Co-Lead review (T-20 to T-14)

The Co-Lead who does not own this consortium reads for: - Factual accuracy - Consistency with own consortia’s reports - Tone appropriate for DFG readership

### 6. PI review (T-14 to T-7)

Send draft to consortium PI for: - Approval of quantitative claims about their consortium - Any additions specific to their work - Sign-off before submission

### 7. Submission (T-7 to T-0)

- Convert to PDF (searchable)

- Submit via consortium’s DFG portal (usually PI’s account)

- Save submitted PDF to Documents/Grants/{acronym}/reports/{YYYY-MM}_progress-report.pdf

- Update Documents/Grants/_tracker.xlsx

- Close Deck card

## 📤 Outputs / Ergebnisse

- Filed progress report (DE + EN if consortium is international)

- Updated grant tracker entry

- Refreshed metrics baseline in Metadata Excel

## ✅ Quality criteria / Qualitätskriterien

- All quantitative claims backed by data source

- PI has approved before submission

- Second Co-Lead has read and signed off

- Submitted before deadline (not on the deadline day)

- Filed with searchable PDF text

## 🔗 Related / Verwandt

- SOP-L01 — Grant Application Preparation (the report reports against the application)

- SOP-A02 — Metadata Excel Maintenance (data source for metrics)

- SOP-B04 — Networking Calendar (deadline tracking)

- SOP-X01 — Annual Consortium Review (may inform report content)

## 📝 Notes / Anmerkungen

- DFG portal quirks: File size limits vary. Test upload at T-3 days.

- Language: German consortia report in DE; international consortia (e.g., EU-linked) sometimes in EN. Match the grant application language.

- Metrics accuracy: Round numbers up to nearest 10 (users) or 100 GB (storage) — avoid false precision.

Change log

| Version | Date | Change |
| --- | --- | --- |
| v1 | 2026-07-28 | Initial version |