# SOP-X03 · Consortium Offboarding

Konsortiums-Abschluss

| Field | Value |
| --- | --- |
| SOP-Code | SOP-X03 |
| Series / Serie | X (Cross-cutting) |
| Owner role / Owner-Rolle | Konsortien-Portfolio (r-consortium) |
| Responsible / Verantwortlich | Co-Lead who owned the consortium |
| Cadence / Kadenz | Per consortium ending / not renewing |
| Status | v1 · 2026-07-28 |
| File / Datei | Documents/SOPs/2026-07-15_cRDM_SOP-X03_Consortium-Offboarding.docx |

## 🎯 Purpose / Zweck

EN: End-of-service process when a consortium’s funded period ends without renewal, or the consortium chooses to leave. Ensures orderly data export, user deactivation, contract closeout, and retention compliance.

DE: Abschluss-Prozess wenn die Förderphase eines Konsortiums endet ohne Verlängerung, oder das Konsortium selbst geht. Sichert geordneten Datenexport, Nutzer-Deaktivierung, Vertragsabschluss und Aufbewahrungsfrist-Konformität.

## 🔔 When to run / Wann anwenden

- Annual review (SOP-X01) concluded no-renewal

- Consortium formally requests to end service

- Grant / funded period ended and no successor grant secured

- Force majeure (rare — regulatory, dispute)

## 👥 Roles (RACI)

| Role | Person(s) |
| --- | --- |
| Responsible | Co-Lead who owned the consortium |
| Accountable | Both Co-Leads |
| Consulted | HA (technical execution), Content-Admin (contract/invoice closeout), consortium PI |
| Informed | Team, other Co-Lead, professors (if consortium was strategically visible) |

## 📥 Prerequisites / Voraussetzungen

- Decision documented (from SOP-X01 or written request from PI)

- Data retention policy on hand (from Terms of Use)

- Contract on hand (for retention clauses, notice periods)

## 📋 Procedure / Vorgehen

### Timeline: 90 days from decision to end-of-service

### 1. T-90 days: Notice + planning

EN: Send formal notice to consortium PI/admin: - Confirm end-of-service date - Explain offboarding process (this SOP, in a short version) - Offer data export in standard formats - Ask for their preferred export handover date - Ask for any special handling requests

DE: Formelle Mitteilung an PI/Admin des Konsortiums: - End-of-Service-Datum bestätigen - Offboarding-Prozess erklären (Kurzfassung dieser SOP) - Datenexport in Standardformaten anbieten - Nach präferiertem Export-Datum fragen - Nach besonderen Wünschen fragen

Create Deck card offboarding-{consortium} with 5 sub-tasks (one per major stage below).

### 2. T-60 days: Data export planning call (30 min)

With PI/admin + HA + Co-Lead. Cover: - What data to export (all, or filtered?) - Format (Nextcloud archive, ZIP, per-group-folder tarball?) - Where to deliver (their own storage, physical HDD, secure transfer?) - Metadata / documentation to include - Any legal / ethics considerations (patient data, sensitive data)

Document decisions in UseCases/{YY-N_acronym}/offboarding/export-plan.docx.

### 3. T-30 days: Perform data export (HA leads)

- HA runs the export following the plan

- Verify integrity (checksum on source vs. exported)

- Deliver to consortium’s chosen destination

- Get written confirmation from consortium: “Export received and verified”

If export takes longer than 7 days for technical reasons, notify PI and slip subsequent milestones.

### 4. T-14 days: User deactivation notice

Send to each user in the consortium’s Nextcloud group: - Personal email (Mareile-sendable) noting end-of-service date - Reminder to download anything they still need - Explanation that after end-date, accounts will be locked (not deleted — see retention below)

### 5. T-0 (end date): User deactivation + service termination

- HA: deactivates users in Nextcloud (do not delete accounts)

- HA: freezes group folder (read-only for 30 days grace period, then archive)

- Content-Admin: sends final invoice (any prorated amount) or credit note (if credit due)

- Co-Lead: sends courtesy close-out email to PI thanking for cooperation

### 6. T+30 days: Grace period end + archival

- HA: moves group folder to cRDM-Archives/ (read-only, retained per policy)

- HA: user accounts moved to disabled-alumni group in Nextcloud

- Metadata Excel updated: status = archived

- Deck card moved to Archived

### 7. T+90 days: Full closeout

- Content-Admin verifies all invoices paid or credits issued

- Final closure document filed: UseCases/{YY-N_acronym}/offboarding/closure.docx

- Contains: dates, decisions, contacts at closure, retention period, next review date

- _tracker.xlsx updated

- Consortium removed from active portfolio in Role Explorer / Task Distribution Register

### 8. Retention period (typically 5 or 10 years, per contract)

- Archive is kept read-only

- Access on request to former PI (if reasonable)

- On retention expiry: separate deletion SOP (not in this SOP)

## 📤 Outputs / Ergebnisse

- Data export delivered + confirmed

- Users deactivated (not deleted)

- Group folder archived

- Final invoice / credit issued

- Closure document filed

- Metadata + trackers updated

## ✅ Quality criteria / Qualitätskriterien

- All timeline stages executed within ±3 days

- PI confirmation received for data export

- No user data lost

- Zero user complaints post-deactivation

- Closure document complete

- Retention plan documented

## 🔗 Related / Verwandt

- SOP-X01 — Annual Consortium Review (triggers this)

- SOP-A07 — User Provisioning (deactivation flow)

- SOP-A05/A06 — Invoice Generation / Payment Tracking (final invoice)

- SOP-L04 — Institutional Escalation (if closure is disputed)

## 📝 Notes / Anmerkungen

- Retention is per contract. Standard cRDM Terms of Use say 10 years for research data. Check the specific consortium contract in case of deviation.

- User accounts stay disabled, not deleted. Deleted accounts break historical audit trails.

- Sensitive data (patient / clinical): may require GDPR-specific handling — consult data protection officer before export.

- Grant-linked consortia: if a DFG grant is still open (report period not closed), consortium cannot fully offboard — keep in winding-down state until grant is closed.

Change log

| Version | Date | Change |
| --- | --- | --- |
| v1 | 2026-07-28 | Initial version |